## Sheet1
Region | Board | Priority Area select from drop down list | Service Area | Reference | Key Deliverable - Name and Description | Key milestones | Progress against deliverables end Sep'22 NOT FOR COMPLETION | Progress against deliverables end Dec'22 NOT FOR COMPLETION | Progress against deliverables end Mar'23 NOT FOR COMPLETION | Lead delivery body | Key Risks | Controls/Actions | Outcome(s) | Major strategies/ programmes the deliverable relates to | Impact of deliverable on health inequalities
West | NHSLan | Urgent and unscheduled care | Corporate | 2022-Lan1 | New USC governance structure embedded across Lanarkshire system to ensure a whole system response to Urgent and Unscheduled Care for our 3 priority areas which are: Acute Front Door Model; RUC including Community care 24/7; and DwD | Implemented by 30 April 2022 |  |  |  | NHSL | Whilst the new structures have been implemented there is a resource gap in supporting the delivery of the Urgent and Unscheduled Care work plans. A Senior Service Improvement Manager post will be advertised in the coming weeks which is critical to our delivery. | Recruitment process underway. Repositioning of post to sit corporately to support whole system working | UC 1 - improving access to unplanned care by directing patients to the right care, at the right place and delivered in the right time | Urgent and Unscheduled Care Collaborative, Our Health Together | The importance of both quantitative service data and qualitative data from communities is recognised. As part of Our Health Together clinical services will be supported to collect and monitor inequalities data in relation to their area to support integrated EQIA. This will include intelligence on access and uptake issues in order to inform targeting of interventions and services to key priority groups.
West | NHSLan | Urgent and unscheduled care | Outpatient Parenteral Antibiotic Therapy (OPAT) | 2022-Lan2 | Interface Care: Cost-effectively Releasing Hospital Bed Capacity through expansion of the Outpatient Parenteral Antibiotic Therapy (OPAT) Service | Three phased business case. Business Case for Phase 1 approved May 2022. Plan to progress Phase 2 of programme via approval governance structures through July 2022. |  |  |  | NHSL | Funding secured is via Interface Care and therefore a non-recurring basis. This means that that recruitment is challenging. | Acute division will carry risk and appoint to posts on a recurring basis. However this may result in post holders being deployed to other parts of the organisation if demonstrable benefits are not realised. | UC 1 - improving access to unplanned care by directing patients to the right care, at the right place and delivered in the right time. Increasing the scheduling of unplanned care. | Urgent and Unscheduled Care Collaborative, Our Health Together | Ensure representation from across our population in co-designing Our Health Together, with help from across the community and voluntary sectors. This includes: patients, carers and those with long-term conditions and disabilities and members of the public who are not currently reliant on regular health and social care support. People who represent black and ethnic minorities and non-native language speakers should also be well represented in our co-design processes. We will also seek to improvement our engagement with children, young people and families. We are also keen to explore opportunities where recruitment goes beyond existing networks to involve people who are not already members of community and voluntary sector organisations. Consideration to be given to the participatory methodologies to be employed to ensure individuals are able to contribute freely. Further develop social prescribing pathways across Lanarkshire in both community and acute settings including investing in the capacity of community and third sector organisations to respond. Recognise importance of both quantitative service data and qualitative data from communities.
West | NHSLan | Urgent and unscheduled care | Respiratory | 2022-Lan3 | Interface Care: Development of Respiratory Whole System Pathway to reduce avoidable presentations, admissions and to facilitate early discharge | Implement Test of Change by 31 October 2022 |  |  |  | NHSL | We know that our Respiratory Nurse Specialists are key to supporting our Hospital @ Home and Telehealthcare developments and we need to undertake some preparatory work to ensure that the team are working in a consistent approach across the organisation. We are also aware that, if TOC are successful, the funding sought for this work is via Interface Care and therefore a non-recurring basis. This means that that recruitment is challenging. | Work is underway with clinical and operational teams to develop and agree a standardised operational model for the Respiratory CNS. This will involve both cultural and practice change which will take time to work through. | UC 1 -Reducing Respiratory admissions across the Lanarkshire system. Increasing self management apporaches, through telehealth, to support people to remain at home and in their commuities. Reducing LOS patients who are admitted with COPD / Respiratory illness. | Urgent and Unscheduled Care Collaborative, Our Health Together | As part of Our Health Together clinical services will be supported to collect and monitor inequalities data in relation to their area to support integrated EQIA. This will include intelligence on access and uptake issues in order to inform targeting of interventions and services to key priority groups.
West | NHSLan | Urgent and unscheduled care | Acute | 2022-Lan4 | USC Priorities Work Plan - Acute Division | Plan agreed by 30 July 2022 |  |  |  | NHSL | Site and system capacity to deliver the plan |  | UC 1 -Enhanced patient flow through sites demonstrated by reduction in time to first assessment and improved 4hour target performance (milestone 85%) | Urgent and Unscheduled Care Collaborative, Our Health Together | The importance of both quantitative service data and qualitative data from communities is recongised. As part of Our Health Together clinical services will be supported to collect and monitor inequalities data in relation to their area to support integrated EQIA. This will include intelligence on access and uptake issues in order to inform targeting of interventions and services to key priority groups.
West | NHSLan | Urgent and unscheduled care | Discharge without Delay | 2022-Lan5 | Discharge Without Delay Workplan | 30/60/90 day action plan in place for reporting to Scottish Government |  |  |  | South Lanarkshire Health and Social Care Partnership | System capacity to support delivery of the key objectives |  | UC 1 - Reduction in delayed discharges; increasing rapid assessment and discharge, developing integrated community care; and care closer to home | Urgent and Unscheduled Care Collaborative, Our Health Together | The importance of both quantitative service data and qualitative data from communities is recongised. Recognise importance of both quantitative service data and qualitative data from communities. As part of Our Health Together clinical services will be supported to collect and monitor inequalities data in relation to their area to support integrated EQIA. This will include intelligence on access and uptake issues in order to inform targeting of interventions and services to key priority groups.
West | NHSL | Urgent and unscheduled care | ED Footprint | 2202-Lan6 | Incresasing UHW ED footprint to enhance flow, staff well-being and patient safety. Initial plans have been agreed by th e clinical and operatonal teams to increase assessment capacity at University Hospital Wishaw front door by 8 spaces. | Ventilation review and design works underway which is essential initial work prior to proceeding with the refurb. Due to the PFI status of UHW this is not a timescale NHS L can control. |  |  |  | NHSL | Continuing to provide a fully operational ED whilst significant refurbishment works are underway. | Securing a modular build which will be position adjacent to ED to facilitate departmental decant. | UC 1 - Improvement in 4 hour target performance; Decreased time to 1st assessment delays; Reduction in complaints due to lengthy ED waits | Urgent and Unscheduled Care Collaborative, Our Health Together | As part of Our Health Together clinical services will be supported to collect and monitor inequalities data in relation to their area to support integrated EQIA. This will include intelligence on access and uptake issues in order to inform targeting of interventions and services to key priority groups.
West | NHSL | Urgent and unscheduled care | Review system wide urgent care provision | 2022-Lan7 | Review of urgent and USC hubs across NHS L including daytime and OOHs provision to inform our understanding of the system gaps and opportunities for further connection and collaboration e.g FNC, Primary Care OOHs, Social Care Hub and Operational Command Centre | Start date to be agreed following disucssions with key stakeholders |  |  |  | NHSL | System capacity to support delivery | Recruitment process underway. Repositioning of post to sit corporately to support whole system working. | UC 1 - improving access to unplanned care by directing patients to the right care, at the right place and delivered in the right time | Urgent and Unscheduled Care Collaborative, Our Health Together | The importance of both quantitative service data and qualitative data from communities is recongised. Recognise importance of both quantitative service data and qualitative data from communities. As part of Our Health Together clinical services will be supported to collect and monitor inequalities data in relation to their area to support integrated EQIA. This will include intelligence on access and uptake issues in order to inform targeting of interventions and services to key priority groups.
West | NHSLan | Recovering planned care | Stroke Neuro - OT. | 2022-Lan8 | Reduction in waiting lists, reduced staff pressure and enhanced patient experience. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | South Rehab Teams - OT | 2022-Lan9 | Reduction in AHP Waiting Times. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis. (b) Regular budgetary monitoring. (c) Existing staff have been offered additional hours (d) Clydesdale staff assisting other localities | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Hand Service - OT. | 2022-Lan10 | Reduction of 300 elective hand surgery cases on waiting list, plus reducing OT legacy waits of 40 weeks. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis for 12 months, rather than the projected 9 months to enhance recruitment opportunities in this specialist area (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | VALPAR Vocational Rehabilitation Service. | 2022-Lan11 | Reducing long waiting times which have resulted as a result of loss of premises through Covid social distancing measures. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available accommodation. | Work ongoing to identify alternative accommodation. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Previous accommodation repurposed to provide additional acute inpatient beds. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Uro Gyn acute Physio capacity. | 2022-Lan12 | Increased omissions of care may result in increased LOS and poorer outcomes for individuals. Need to reduce waiting times. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Acute Physio capacity. | 2022-Lan13 | Increased omissions of care may result in increased LOS and poorer outcomes for individuals. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Community Rehab - Physio. | 2022-Lan14 | To deal with Covid consequences which have led to considerable waiting times - Hamilton 244 waiting, longest wait 29 weeks; EK 198 waiting, longest wait 14 weeks; Clydesdale 85 waiting, longest wait 10 weeks; Camglen 60 waiting , longest wait 8 weeks. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Pulmonary Rehab - Physio. | 2022-Lan15 | Provide service commensurate to need linked to ongoing service development re long Covid. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Respiratory - Physio. | 2022-Lan16 | Provide service commensurate to need linked to ongoing service development re long Covid. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Amputee - Physio. | 2022-Lan17 | To recover service waiting times to ensure maximum rehabilitation opportunities and associated access to limb fitting. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a fixed term basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | MSK - Physio. | 2022-Lan18 | Reduced access to core MSK services can lead to increased attendances at both ED and GP practices as a result. Recovery of this service to pre-pandemic levels will support flow through both primary and secondary care services. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Nursing: Treatment Rooms. | 2022-Lan19 | This is to help meet the increased need of patients being sign-posted to the treatment rooms for phlebotomy (missed due to Covid-19) and increased complexity of conditions such as leg ulcers. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Nursing: School Nursing. | 2022-Lan20 | To assist with recovery of Primary 1 assessments missed due to Covid-19 disruption. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Nursing: District Nursing. | 2022-Lan21 | To support the elimination of the backlog of patients due to Covid consequences plus caring for end of life patients previously managed by care at home staff. This will also release care at home staff to manage more patietns from the hospital/reduce DDs. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Nursing: Palliative Care. | 2022-Lan22 | To support the elimination of the backlog of patients due to Covid consequences plus supporting more end of life patients at home. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Nursing: MS/ Neuro. | 2022-Lan23 | To support the elimination of the backlog of patients due to Covid consequences plus support to end of life patients. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Social care | CAReS. | 2022-Lan24 | To support the elimination of the backlog of patients due to Covid consequences plus long term condition and reduced functioning capacity patients. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Diabetes Nursing. | 2022-Lan25 | To support the elimination of the backlog of patients due to Covid consequences and continue to support reducing OPD waiting times. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recruitment and retention | Nursing: Health and Homeless. | 2022-Lan26 | To support the elimination of the backlog of patients due to Covid consequences. This will also support increased reduction of respective inequalities associated with this vulnerable group of patients. Recruitment of staff specifically introduction of the through care and after care post. There is daily safe staffing review documented through the PRAG. | In progress. |  |  |  | South Lanarkshire Health and Social Care Partnership | (a) Lack of available staffing. (b) Recruitment to permanent posts is a significant financial risk. | (a) Posts have been advertised on a permanent basis to assist in staff recruitment. (b) Regular budgetary monitoring. (c) Escaltion of real time staffing risk via PRAG | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of service | Management of waiting times - work is ongoing to describe recovery trajectory linked to same. | By improving access to services for all then so this reduces the likelihood for people to suffer inequality as a result of reduced access.
West | NHSLan | Recovering planned care | Addiction Recovery Teams | 2022-Lan27 | Recovery of performance targets, reporting on the MAT standards, completion of mapping | people accessing services have the option to start MAT from the same day of presentation, people are supported to make an informed choice on what medication to use for MAT, and the appropriate dose, people at high risk of drug-related harm are proactively identified and offered support to commence or continue MAT |  |  |  | North Lanarkshire Health and Social Care Partnership | Drug related harm or death | ADP monitoring perfomance locally and nationally | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of servic | ADP Strategic Plan | Impact on the most marginalised in our communities
West | NHSLan | Social care | Care at Home | 2022-Lan28 | Resilience in Care at Home | Assessment and Unmet Need |  |  |  | North Lanarkshire Health and Social Care Partnership | Delay in identifying and commencing service | Planned Date of Discharge in place and Home Assessment Team created | SC1. Improving access to social care and delivering more integrated, safe, effective and efficient services. | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23 | Reducing inequality through new models of care
West | NHSLan | Recovering planned care | Perinatal and Maternal Mental Health | 2022-Lan29 | Support women and babies in a range of ways in identifying and managing mental heath problems | Women/primary caregivers who use the service experience improved mental wellbeing |  |  |  | North Lanarkshire Health and Social Care Partnership | covid related impact on recruitment and engagement with stakeholders, especially people with lived experience | Monitoring of risk through the PIMH risk register | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23: Mental Health Recovery Strategy; Mental Health and Wellbeing Strategy Lanarkshire 2019-2024 | Reducing inequality through revised pathways
West | NHSLan | Social care | Mental Health Officer Service | 2022-Lan30 | Providing statutory mental health officer service | Meeting statutory timescales for MHO service |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention of MHOs | Workforce planning nationally and locally | RR1. Continue to focus on workforce growth. | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23: Mental Health Recovery Strategy; Mental Health and Wellbeing Strategy Lanarkshire 2019-2024 | Impact on the most marginalised in our communities
West | NHSLan | Recovering planned care | Psychological Services | 2022-Lan31 | Providing phychological therapies | 90% of patients commence an evidenced based psychological therapy within 18 weeks of referral |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monitoring of performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23: Mental Health Recovery Strategy; Mental Health and Wellbeing iStrategy Lanarkshire 2019-2024 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | CAMHS | 2022-Lan32 | provide a wide range of services designed to support children, young people and families experiencing mental health difficulties | recover to 90% performance in 18 week RTT by March 2023 |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | CAMHS recovery Board in place monitoring progress and performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services, RR1. Continue to focus on workforce growth. | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23: Mental Health Recovery Strategy; Mental Health and Wellbeing iStrategy Lanarkshire 2019-2024 | Reducing inequality through new models of care
West | NHSLan | Recovering planned care | Paediatrics | 2022-Lan33 | medical in patient service | Recovery of performance to 90% waiting within 12 weeks |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Paeds recovery board in place to monotor rogress and performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23: Children's Services Plan | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | SLT ALD | 2022-Lan34 | Specialist assessment and support with communication and swallowing | Recovery of perfromance to 90% waiting within 12 weeks |  |  |  | North Lanarkshire Health and Social Care Partnership | Rectuitment and retention, increase in demand | Refresh of information management systems to increase performance monitoring | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | SLT CYP | 2022-Lan35 | Specialist assessment and support with communication and swallowing | Recovery of performance to 90% waiting within 12 weeks |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Refresh of information management systems to increase performance monitoring | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkhsire Health and Social Care Strategic Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | Sexual Health | 2022-Lan36 | Specialist sexual health services to young people and adults | Recovery of performance targets |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monotoring performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | The service is geared to address inequalities gaps, in terms of work being done with Homeless patients, deprived patients and those in challenging situations (abusive relationships etc) and also young people in care
West | NHSLan | Recovering planned care | Osteoporosis and Fracture Liaison | 2022-Lan37 | Specialist osteoporosis and fracture service | Recovery of performance to 12 weeks waiting times |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Recovery plans based on full staffing are being monitored | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | Continence Service | 2022-Lan38 | Specialist continence support | Recovery of performance to 9 weeks waiting times |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increase in demand | Recovery plans based on full staffing are being monitored | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategic Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | Dietetics | 2022-Lan39 | Specialist dietetic support | Recovery of performance to 12 weeks waiting times |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monitoring performance through the Waiting Times Capacity Planning Group | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Sustainability and value | Prisoner Healthcare | 2022-Lan40 | Comprehensive health care to prisoners in Shotts Prison | Recovery of performance |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monitoring of performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | Weight Management | 2022-Lan41 | Weight Management Service | Delivered in line with the Scottish Government’s Diet & Healthy Weight Delivery Plan, Physical Activity Delivery Plan and Type II Diabetes Framework and to meet the requirements of the Minimum Standards for Weight Management, Common Milestones, and Standardised Core Dataset collection |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monotoring of performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services, RR1. Continue to focus on workforce growth. | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | Maternal and Infant Nutrition | 2022-Lan42 | Healthy lifestyles in pregnancy service | Delivered in line with Scottish Government guidelines |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monitoring of performance and inclreased use of digital connection | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Recovering planned care | Tobacco Control Programme | 2022-Lan43 | Tobacco control programme | Prevention and Protection elements of the Tobacco Control programme |  |  |  | North Lanarkshire Health and Social Care Partnership | Recruitment and retention, increased demand | Monitoring ot performance | PC1. Maximise planned care activity, taking full advantage of the opportunities to transform the delivery of services | North Lanarkshire Health and Social Care Strategy Commissioning Plan 2020-23 | Reducing inequality through timeous service intervention
West | NHSLan | Staff wellbeing | Absence management reporting | 2022-Lan44 | Reduce sickness absence rate. | Continue to manage sickness absence in accordance with Once for Scotland policy to aim for 4% sickness absence target. Metric: 4% target or under = Green, 4-6% = Amber, Over 6% = Red |  |  |  | NHSL | Unknown impact of Covid outbreaks and severity of flu over winter. | Active attendance management policy implementation. | SW1. Looking after our people and helping them to recover. | NHS Recovery Plan | To improve staff wellbeing and ensure staff are supported to return to work.
West | NHSLan | Recruitment and retention | International recruitment | 2022-Lan45 | Increase international recruitment rate. | Work to build capacity for international recruitment. Metric: To be determined once investment and infrastructure have been confirmed. |  |  |  | NHSL | Unconfirmed investment and infrastructure to support. | Actively pursuing international recruitment in partnership with agencies. | RR1. Continue to focus on workforce growth. | NHS Recovery Plan, National Workforce Strategy for Health and Social Care | Increase the deployable resource to support NHS Lanarkshire's population.
West | NHSLan | Recruitment and retention | Development of Employability strategy | 2022-Lan46 | Deliver NHSL's Employability Strategy. | Deliver NHSL's Employability Strategy by March 2023. Metric: To be determined once investment confirmed. |  |  |  | NHSL | Demonstrator project -risk that won't be able to recruit to all 30 placements due to lack of applicants. | Currently recruiting to NHS Demonstrator project, and have 30 placements identified with a proposed start date of 18th September. To look at further employability opportunities, a joint session has been scheduled for August to allow a more detailed look at joint work around improve local employability including pathways to employability and care academy approaches, to ascertain what more can be done collaboratively. | RR1. Continue to focus on workforce growth. | National Workforce Strategy for Health and Social Care | Widening access to NHS employment through employability initiatives and pre-employment programmes.
West | NHSLan | Recruitment and retention | Registered Nursing/Midwifery Vacancy Rates | 2022-Lan47 | Reduce vacancy rate for registered Nursing/Midwifery staff. | Target to reach vacancy level of less than 5% for registered Nursing/Midwifery staff. Metric: 5% target or under = Green, Between 5-7.5% = Amber, Over 7.5% = Red |  |  |  | NHSL | Availability of registered nurses and midwives nationally. | NHSL's refined process for newly qualified nurses, for staff to commence as B4 until they receive their registration. | RR1. Continue to focus on workforce growth. | NHS Recovery Plan, National Workforce Strategy for Health and Social Care | Increase the deployable resource to support NHS Lanarkshire's population.
West | NHSLan | Sustainability and value | Health and Care (Staffing) (Scotland) Act 2019 | 2022-Lan48 | Complete self-assessment return to Healthcare Improvement Scotland (HIS) for health care staffing act readiness in quarter 4 of 22/23 and develop plan to reach full green status for readiness by April 2024. | Metric: In line with RAG status within nationally developed self-assessment template. |  |  |  | NHSL | Current vacancy levels and reliance on nursing premium rate agency may hamper our ability to be fully compliant by April 2024. | We are regularly monitoring agency usage across the board and actively recruiting to outstanding vacancies where supply allows. | VS1. We deliver within available resources and achieve financial balance. | Health and Care (Staffing) (Scotland) Act 2019, NHS Recovery Plan and National Workforce Strategy for Health and Social Care | Ensures safe staffing is enshrined across all of NHS Lanarkshire.
West | NHSLan | Sustainability and value | Monklands Replacement Project -Outline Business Case (OBC) | 2022-Lan49 | To deliver an outline business case for MRP which provides value for money and a hospital for the future. | Develop indicative workforce requirements in partnership with service leads and staff side representatives based on new hospital healthcare planning assumptions. Metric: To be determined once investment confirmed. |  |  |  | NHSL | Workforce affordability and availability. | Undertake workforce scenario based planning in close collaboration with associated professional and service leads which will be evaluated based on affordability, adaptability and availability for approval by NHS Lanarkshire Board ahead of OBC submission. | VS1. We deliver within available resources and achieve financial balance. | Health and Care (Staffing) (Scotland) Act 2019 and National Workforce Strategy for Health and Social Care | Delivering a state of the art hospital for the people of Lanarkshire.
West | NHSLan | Sustainability and value | Realistic Medicine | 2022-Lan50 | 1. Develop strategy that aligns RM principles in outpatient waiting list | Q1- identify clinical lead and one area to start Q2/3- -spread into another specialty area Q4- develop strategy from work |  |  |  | NHS Lan | Delay to progress if there is further pandemic interuptions that reduces opportunity to work with clinical team | To align work with recovery mobilisation work streams | VS2 | Realistic Medicine Strategy | Practising Realistic Medicine can help us deliver a change in culture and to working with people in shared decision making enabling their choice whether a treatment or an investigation is going to be of personal value.
West | NHSLan | Sustainability and value | Realistic Medicine | 2022-Lan51 | 2. Develop strategy that aligns RM principles in inpatient surgical waiting lists | Q1- identify clinical lead and one area to start Q2/3- -spread with other specialty area Q4- develop strategy from work area |  |  |  | NHS Lan | Delay to progress if there is further pandemic interuptions that reduces opportunity to work with clinical team | To align work with recovery mobilisation work streams | VS2 | Realistic Medicine Strategy | Practising Realistic Medicine can help us deliver a change in culture and to working with people in shared decision making enabling their choice whether a treatment or an investigation is going to be of personal value.
West | NHSLan | Sustainability and value | Realistic Medicine | 2022-Lan52 | 3. Develop consultation pathways with all health care professionals that inlcude virtual/telephony consultation, ACRT and patient initiated returns | Q1- identify clinical lead and two long term conditions Q2/3- -develop baseline measure and measurement plan Q4- develop pathway strategy |  |  |  | NHS Lan | Delay to progress if there is further pandemic interuptions that reduces opportunity to work with clinical team | To align work with recovery mobilisation work streams | VS2 | Realistic Medicine Strategy | Practising Realistic Medicine can help us deliver a change in culture and to working with people in shared decision making enabling their choice whether a treatment or an investigation is going to be of personal value.
West | NHSLan | Sustainability and value | Realistic Medicine | 2022-Lan53 | 4. Develop resources to support Health and Social Care Workforce in practising Realistic Medicine | Q1- identify champions across HSCP. Q2/3- -Build on network connections, intranet, webpage, Turas learning Q4- hold annual conference bringing together innovation & improvement projects |  |  |  | NHS Lan | Delay to progress if there is further pandemic interuptions that reduces opportunity to work with clinical team | To align work with recovery mobilisation work streams | VS2 | Realistic Medicine Strategy | Practising Realistic Medicine can help us deliver a change in culture and to working with people in shared decision making enabling their choice whether a treatment or an investigation is going to be of personal value.
West | NHSLan | Sustainability and value | Realistic Medicine | 2022-Lan54 | 5. To support Shared Decision Making processes by enhancing patients, carers, families and staff in realistic conversations. . | Q1- Identify four community areas to test ReSPECT, enhance ACP's and implement revised TEP in all three acute hospitals Q2/3- -build on e-KIS upload, align with national workstream for ReSPECT APP and develop & test SDM evaluation tool Q4- audit and evaluate impact for ReSPECT/ACP and SDM |  |  |  | NHS Lan | Delay to progress if there is further pandemic interuptions that reduces opportunity to work with clinical team | To align work with recovery mobilisation work streams | VS2 | Realistic Medicine Strategy | Practising Realistic Medicine can help us deliver a change in culture and to working with people in shared decision making enabling their choice whether a treatment or an investigation is going to be of personal value.
West | NHSLan | Digital Strategy and Delivery | Board Area | 2022-Lan55 | eHealth Programme | The eHealth Programme comprises of a wide range of projects including; HEPMA, eOBS, Community IT, EPR, Order Communications, GP IT and M365. There are also a range of smaller projects and Infrastrucure projects e.g. OOH Cloud Migration, TrakCare Cloud Migration and Unified Communications (Telephony). The programme has formal governance and reporting arrangements within the Board. |  |  |  | eHealth Executive Group | Individual projets and the programme retain a risk register none of the risks have been esclated to the Corporate Risk Register. | In line with the NHSL Risk Management Stategy all risks have risk owners, risks are reviewed on a regular basis at the relevant oversight group/s. |  | This is a core element of the local/national digital health and care strategy.
West | NHSLan | Digital Strategy and Delivery | Board Area | 2022-Lan56 | Cyber Security Workplan | The Cyber Security Workplan has been established to deliver a programme work to support the Board meeting its obligations as set out in the Strategic Framework for a Cyber Resiliant Scotland. The workplan is focused on the NIS Directive (and targets) and achieving Cyber Essential Plus. |  |  |  | eHealth Executive Group | There is a risk that both nationally and locally we will fail to create sufficient funds available to meet the challenging areas related to NIS and CE+ which will require further investment in staff, services and associated cyber security tools. | In line with the NHSL Risk Management Stategy all risks have risk owners, risks are reviewed on a regular basis at the relevant oversight group/s. |  | This is a core element of the local/national digital health and care strategy.
West | NHSLan | Digital Strategy and Delivery | Board Area | 2022-Lan57 | Information Governance Workplan | The Information Governance Workplan has been established to deliver a programme work to support the Board meeting its obligations as set out in the Data Protection Act / GDPR. |  |  |  | eHealth Executive Group | The Infromation Governance Committee maintains a risk register none of the risks have been esclated to the Corporate Risk Register. | In line with the NHSL Risk Management Stategy all risks have risk owners, risks are reviewed on a regular basis at the relevant oversight group/s. |  | This is a core element of the local/national digital health and care strategy.
West | NHSLan | Digital Strategy and Delivery | Board Area | 2022-Lan58 | Digital Strategy Development | Following the recent publication of the national digital health and care startegy NHS Lanarkshire will publish a new digital strategy in early 2023 covering the period 2023-28 including a five year delivery plan this will underpin the Laanrkshire healthcare strategy being developed "Our Health Together". |  |  |  | eHealth Executive Group | None. |  |  | This is a core element of the local/national digital health and care strategy.
West | NHSLan | Recovering planned care | Outpatient Capacity | 2022-Lan59 | Insourcing outpatient capacity (from May 2022); 1. Gastroenterology 2. Dermatology 3. Rheumatology 4. Respiratory 5. Neurology 6. Ophthalmology | Trajectories for Q2 to Q4 subject to ongoing review following guidance on revised timescales for reduction of long waits. 1. Provision of 21,100 outpatient appointments 2022-2023 (5,275 per Quarter). 2. Eliminate Outpatient waits times over 2 years by Aug 2022 3. Eliminate outpatient waiting times over 18 month by Dec 2022 4. Eliminate outpatient waiting times over 12 months by Mar 2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Outpatient Capacity | 2022-Lan60 | Internal outpatient Waiting List Initiatives (WLI) from May 2022 (across specialties) | Trajectories for Q2 to Q4 subject to ongoing reviewed following guidance on revised timescales for reduction of long waits 1. Provision of 9,362 additional outpatient appointments 2022-2023. 2. Eliminate Outpatient waits times over 2 years by Aug 2022 3. Eliminate outpatient waiting times over 18 month by Dec 2022 4. Eliminate outpatient waiting times over 12 months by Mar 2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Inpatient / Day Case Capacity | 2022-Lan61 | Outsourcing to external capacity Inpatient / Day Case from May 2022; 1. Gynaecology 2. Orthopaedics 3. General Surgery 4. Ophthalmology 5. OMFS | Trajectories for Q2 to Q4 subject to ongoing review following guidance on revised timescales for reduction of long waits 1. Provision of 3,060 inpatient / Day Case procedures 2022-2023. 2. Eliminate TTG waits times over 2 years by Sept 2022 3. Eliminate TTG waiting times over 18 month by Sept 2023 4. Eliminate TTG waiting times over 12 months by Sept 2024 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Inpatient / Day Case Capacity | 2022-Lan62 | Provision of Inpatient and Day Case Waiting list Initiatives from May 2022 across 3 hospital sites | Trajectories for Q2 to Q4 subject to ongoing review following guidance on revised timescales for reduction of long waits. 1. Provision of 1,068 inpatient / Day Case procedures 2022-2023. 2. Eliminate TTG waits times over 2 years by Sept 2022 3. Eliminate TTG waiting times over 18 month by Sept 2023 4. Eliminate TTG waiting times over 12 months by Sept 2024 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Inpatient / Day Case Capacity | 2022-Lan63 | Inpatient / Day case Allocation at Golden Jubilee from April 2022; 1. Orthopaedics 2. General Surgery 3. Ophthalmology 4. Endoscopy | Through 2022-2023 the following allocation has been provided to NHS Lanarkshire. The focus will be on the reduction of long waiting times however these allocations are likely to be reallocated over Q2-Q4; 1. Orthopaedics (696) 2. General Surgery (281) 3. Ophthalmology (2,130) 4. Endoscopy (1,339) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | External inpatient Capacity (Orthopaedics) | 2022-Lan64 | Access external Orthopaedic Capacity at Kings Park to treat long waiting patients | 1. Provision 54 day case in and 10 joint Q1 and 32 orthopaedic Joints Q2 2. Focus on elimination long waits in Orthopaedics |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Inpatient / Day Case Capacity | 2022-Lan65 | Insource theatre staffing to increase core theatre capacity from June 2022 | Tender for 3 theatres teams (awarded to Sirona) to treat; 1. Team 1 - ENT Procedures (Q1) 2. Team 2 - Urology Procedures (Q2) 3. Team 3 - General Surgery and Gynaecology Procedures (Q3) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Inpatient / Day Case Capacity | 2022-Lan66 | Redesign of Orthopaedic Theatre at UH Hairmyres | Capital work to increase size orthopaedic theatre and improve flow of patients (theatre efficiency) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Increase Ophthalmology capacity | 2022-Lan67 | Investment in theatre staffing to provide additional capacity within surgicube at UH Hairmyres | Provision of an additional 3 sessions per week utilising surgicube, 376 procedures through 2022-2023 (96 patients per quarter) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Core Outpatient Capacity | 2022-Lan68 | Return to pre covid levels of Outpatient activity | Return to 100% of pre covid outpatient activity by September 2022 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Core Theatre Capacity | 2022-Lan69 | Return to Pre covid levels of Theatre operating capacity | Return to minimum 90% of pre covid theatre operating capacity by March 2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Theatre Capacity (Robotics) | 2022-Lan70 | Implement Robotic Assisted Surgery (RAS) in Colorectal and Urology within NHSL | 1. Implement RAS In Colorectal Surgery by June 2022 2. Implement RAS in Urology Surgery by August 2022. 3. Utilise ERAS principles in patient care 4. Demonstrate improved outcomes and patient experience |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 2 | West of Scotland Regional Robotics Programme | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Waiting List Management | 2022-Lan71 | Maintain 3 stage validation and management of waiting lists in line with access policy | 1. Ensure that timely validation is maintained on all outpatient and treatment waiting lists. 2. Application of access policy and national definitions of reasonable offers, removals and unavailability |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Capacity Planning | 2022-Lan72 | Ensure robust waiting list reporting (national and local), waiting times modelling and capacity planning | Ongoing funding for Analyst within information services team |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Gynaecology Myosure | 2022-Lan73 | Provide in-patient operative and one-stop out-patient clinics in NHS Lanarkshire to encompass assessment, pelvic ultrasound, hysteroscopy, IUS insertion and “see-and-treat” myosure for women with abnormal heavy menstrual and postmenopausal bleeding (cancer and pre-cancer). | Provision of 700 outpatient / day case treatment slots (175 per quarter) through 2022 - 2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Neurology | 2022-Lan74 | Phased redesign of Neurology services, increasing core outpatient capacity and nurse led activity within NHSL | Phase 1 includes recruiting; 1. 2.00 WTE Band 7 Nurses 2. 6 PA Consultant sessions 3. 1.00 WTE Band 3 Clerical Officer Expected to deliver 780 New and 2,124 Return appointments |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Orthopaedics | 2022-Lan75 | Recruit Surgical First Assistants in Orthopaedics to protect elective orthopaedic capacity | 1. Appoint 2.00 WTE Surgical first assistants 2. Fill Rota gaps to run 6 Elective Orthopaedic theatre sessions |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Orthopaedics (Long Waits) | 2022-Lan76 | Expand Orthopaedic Scheduling team to facilitate review, clinical prioritisation and health screening of long waiters in Orthopaedics. Facilitate efficient allocation and utilisation of Orthopaedic (internal and external) capacity | Recruit A&C Staff; 1.00 WTE Band 3 1.00 WTE Band 4 1.00 WTE Band 5 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 2 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Endocrine (Outpatients) | 2022-Lan77 | Recruit Band 6 Clinical Nurse Specialist to the Endocrine Service to address increasing demand and prevalence in long term conditions | Clinical Nurse Specialist expected to see 35 New and 350 Returns per quarter (Q3 and Q4) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Anaesthetics | 2022-Lan78 | Support increase in Orthopaedic elective lists, improve theatre utilisation and patient safety. Enhance training and workforce | Recruit 2 Anaesthetic Associate posts |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Dermatology | 2022-Lan79 | Recruit Pharmacy staff to staff return Dermatology patient caseload | 1. Recruit 0.6 WTE Band 8a Pharmacist 2. Recruit 0.4 Band 7 Pharmacists 3. Establish Return Clinics from June 2022 4. Expected to divert 2,500 patients per year from Consultant clinics (625 patients per quarter) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology Ultrasound | 2022-Lan80 | Provide Regular waiting lists staffed by NHS Lanarkshire and Locum sonographers | Provision of 4,000 additional ultrasound appointments (1000 patients per quarter) through 2022 -2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology CT | 2022-Lan81 | Provision of a Staffed mobile CT from 24th July 2022 for 6 weeks to reduce waiting lists. | Delivery of staffed mobile van - expected 24th July 22 for 6 weeks providing 1,200 additional appointment slots |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology CT | 2022-Lan82 | Second CT scanner at UHM to increase NHS Lanarkshire CT capacity | Procurement and Implementation of 2nd permanent CT scanner at UH Monklands |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology CT | 2022-Lan83 | Undertake internal CT waiting lists to reduce waiting times | Provision of additional 1,100 CT appointments (275 patients per quarter) through 2022-2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology MRI | 2022-Lan84 | Undertake internal MRI waiting lists to reduce waiting times | Provision of an additional 400 MRI slots (100 patients per quarter) through 2022 -2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology MRI | 2022-Lan85 | Recruit additional staff to facilitate 7 day working at UHW | Recruitment of; 1. 1.0 WTE Band 6 Radiographer 2. 0.4 WTE Band 3 HCSW |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Radiology General x-rays | 2022-Lan86 | Return to full open access for GP plain films Chest X-Ray April 2022 expand to plain film from August 2022 | Provide open access to NHSL GP's from August 2022 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Endoscopy | 2022-Lan87 | Establish weekly clinic for Cytosponge expanding patient criteria to include Patients with Dysphagia | provide 248 appointments (62 patients per quarter)over 2022-2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Endoscopy | 2022-Lan88 | Continue to utilise Colon Capture | Provide 180 appointments (45 patients per quarter)over 2022-2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Endoscopy | 2022-Lan89 | Refurbishment of UH Monklands Endoscopy rooms (ventilation) | Provide core capacity of 960 sessions (24 weeks) from October 2022 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Endoscopy | 2022-Lan90 | Dual mobile endoscopy unit from Vanguard located at UH Hairmyres | Expected to provide 4176 Endoscopy appointments (1044 patients per quarter) over 2022 / 2023 |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | NHS Lanarkshire Recovery Plan | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - SACT | 2022-Lan91 | Expand SACT services to meet increasing demand fro both oral and IV therapies. | 1. Recruit 2x Band 7 Tech (Aseptic) and 2x Band 5 (Day Surgery) 2. Sustain and expand Non Medical Prescribing 3. Repatriate up to 400 (upper GI) Cancer patients per year from Regional Cancer Centre (Glasgow) |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Urology (Radiology) | 2022-Lan92 | WLI to be carried out for MRI prostates to provide additional capacity | 1. Establish 2 dedicated MRI sessions per month (12 patients). 2. Reduce the waiting time to below 4 weeks. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Colorectal /Upper GI (Endoscopy) | 2022-Lan93 | Admin resource to support ongoing service improvements introduced during COVID 19 including Qfit testing. | 1. Ongoing funding 1.00 WTE Band 4, 2 WTE Band 3 and 1.00 WTE Band 2 2. Support alternative pathway diverting up to 5,000 patients away from endoscopy. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Surgery (Pre-assessment) | 2022-Lan94 | Increase in consultant provision within the pre-assessment service targeted to patients with cancer. This would equate to 6 additional anaesthetic consultant sessions per week (2 per site). | Preassessment is a bottle neck to delivery of surgical intervention for cancer treatment. Increasing Consultant Anaesthetist presence will decrease the time it takes to complete preassessment ensuring patients are ready for Surgery within 4 weeks. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Endoscopy | 2022-Lan95 | Purchase of 2 PCF-H290T1 operating colonoscopies (£83,417.04)and 1 ERBE 300 vio (£20,763.77).to improve the safety and delivery of endoscopic resection of large colorectal benign lateral spreading tumours and early cancer. | Improving patient safety, reduced procedure time and better patients outcomes ( patient avoid resection and stoma). Expected to facilitate 6 procedures per month |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - ECDC (vague Symptoms) | 2022-Lan96 | Provide rapid patient centred pathways for patients with vague symptoms suggestive of cancer that do not fit within existing cancer pathways. Develop pilot programme in conjunction with primary care | Provide rapid patient centred pathways for patients with vague symptoms suggestive of cancer that do not fit within existing cancer pathways. 1. Recruit; • 1.00 WTE Band 7 • 2 PA of clinician • 1.00 WTE Band 4 Co-ordinator/Navigator 2. Provide 5 CT slots per week for NHSL outsourced to MEDICA 3. Ensure patients are on the correct pathway within 2 week |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 3 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Patient Tracking | 2022-Lan97 | Effective and reliable tracking aligned to the National Framework with escalations to teams. Anticipated improvements within the 62 day performance due to robust communication and escalation. | Recruit additional 2.0 wte band 4 cancer trackers to the Tracking Team. This will supporting improving tracking from day 1 for all cancer patients with timely escalations within the diagnostic element of the pathways. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Upper GI | 2022-Lan98 | The additional hours of the Nurse consultant cover scheduled and unscheduled leave and support oncology clinic with nmp sessions. Hours also included backfill for current staff member to develop advance practise skill set. | Additional clinical hours within the Upper GI CNS Team- 0.8wte band 6. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Colorectal | 2022-Lan99 | Support the robust sustainability within the surgical element of the CNS role . This will ensure patient experience is not impacted and patient expectation will be sustained with continuous support and link to CNS. | Additional clinical hours within the Colorectal CNS Team- 0.4wte band 6. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Non Medical Prescribers (NMP) | 2022-Lan100 | Support Non Medical Prescriber (NMP) model that is sustainable and align to oncology clinic. This will in turn support the further development of clinic templates that are more aligned to meet the growing demand supported with various skill sets utilising advance practice skill set and the ability to stratify patients inclusive of methods of assessment- telephone, attend anywhere and F2F. | Introduction of 1.0 wte band 7 NMP role that will sustain and support oncology clinics |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Service Improvement | 2022-Lan101 | The focus of a service improvement role to work with team to ensure measure are in place to support monitoring of the impact of cancer improvement work will support reliable data moving forward to demonstrate the impact and requirement of recurring funding due to service model progression and support clinical teams with service redesign. | Introduction of 1.00 WTE band 7 service improvement Co-ordinator. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Cancer - Head and Neck / Upper GI | 2022-Lan102 | Sustain waiting time for dietetic assessment for H&N and upper GI patients. Facilitate telephone / remote review and triage. Improve nutrition status before, during and after treatment. Improve QOL and ensure key data around MUST is recorded to support MUST score. | Year 2 funding of a Band 3 support worker role within the H&N and Upper GI dietetic team |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 1 | National Cancer recovery Framework | Provided improved access to treatment through increasing internal and external capacity in line with patient priority and health needs.
West | NHSLan | Recovering planned care | Prehabilitation in cancer care | 2022-Lan103 | Prehabilitation session focuses on physical, psychological and nutritional health behaviour change, with further ongoing free psychology, exercise and nutrition sessions offered at Maggie’s and more widely to support ongoing change. | A Prehab session will last 90 minutes, and participants would attend 1 session prior to surgery or the start of treatment, plus additional ongoing support sessions (e.g. exercise, nutrition, psychology). |  |  |  | Maggie's Lanarkshire | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 2 | National Prehabilitation Programme Framework for Effective Cancer Management Recovery and Redesign: An Action Plan for Cancer Services | Opportunity to undertake holistic assessment for each individual person referred to the service that will not only focus on prehabilitation before commencing treatment will include and focus on income, education on their cancer along with signposting to ongoing support.
West | NHSLan | Recovering planned care | Digital Follow Up in Prostate cancer | 2022-Lan104 | Urology Optimal pathway…use of emerging technologies to support patient initiated review (PIR) | Current secondary care follow up extends to ten years post radical treatment (prostatectomy or radiotherapy) with clinic visits on a 6 -12 monthly frequency. Management of PSA remotely would realise a reduction in the number of clinic DNAs, associated costs for reappointment and knock on impact on CWTs. |  |  |  | NHSL - Acute | As per Corporate / Acute Risk Register: Workforce - Recruitment challenges and staffing gaps across major staffing groups, Pressure from ongoing unscheduled care admissions (beds / staffing), Limitations on physical capacity, COVID / Winter pressures (beds / staffing), Financial pressure | Ongoing Recruitment and retention, Staff Welfare, Application of new ways of working, Application of evolving Infection control guidance, Maximising external / Internal Capacity, Funding application to SG | PC 2 | Regional Planned Programme of work Framework for Effective Cancer Management Recovery and Redesign: An Action Plan for Cancer Services Local service Improvement- Prostate pathway work. Centre for Sustainable Delivery. National Pathways within the Connect me Programme. | The patients journey will be improved in a number of ways: Act as a single point of access for patients who are on self-managed follow up pathways. Standardised managed electronic process for early identification of possible recurrence in the target patient group and sign-posting to clinical team to fast track patients for specialist review. Reduction of any variations in care across the region depending on local board and HSCP arrangements for phlebotomy services. Improve clinical outcomes and survival data. Minimise financial and time constraints associated with patient travel for clinic visits. Empower more patients in management of their follow up.
Note on C1: u452026: Please clearly indicate which of the five priority areas laid out in the planning guidance each deliverable relates to. You will be able to select one of the five areas from a drop down list in each cell of this column.
Note on D1: u452026: Please subdivide the plan into groups of deliverables which are meaningful and useful for your Board. These will not necessarily correspond to SG Health Policy Areas so it is helpful if you mention any policy areas or specific plans/strategies relevant to deliverables in the column provided for related plans/strategies. For example: Primary Care; Mental health; Digital; Cancer care
Note on E1: u452026: Please assign a unique reference number/code to each deliverable. This will also provide a shorthand to refer to deliverables in any supporting narrative or when making cross-references between deliverables. Pleases use the following format: e.g. 2022-BOR1; 2022-AA1; 2022-HIS; 2022-Lan45; 2022-Ork4
Note on F1: u452026: This should be a title/name or short description of the deliverable. This is an important field for analysing similar deliverables across Plans.
Note on G1: u452026: Highlight here at key points you will be tracking progress. What are you expecting to deliver and by when?
Note on K1: u452026: indicate where the Lead Delivery Body is not the Health Board, for example a HSCP.
Note on L1: u452026: You don't need to include much detail here. This field is primarily for cross Scotland analysis so a simple list is preferable. Where risks correspond to your corporate risks or Risk Register, please do include a title for the risk (rather than a number) to enable cross-comparison
Note on M1: u452026: Same as left, not much detail needed, a simple list preferred
Note on N1: u452026: Please highlight here which of the outcomes outlined in the guidance this deliverable contributes to. Please us the code outlined in the guidance
Note on O1: u452026: Include details where your deliverables contribute to or deliver against national approaches, plans and strategies, or your own published Strategies or Strategic/Service Plans. Where there is no specific plan or strategy, you could flag up the SG Policy Team that your teams work most closely with, or a particular funding stream. You can include more than one plan/strategy etc., in this column as required. The plans etc., listed here could be local or national in scope (or both). You may wish to flag delvierables where they link to other national strategies
Note on P1: u452026: Please provide a brief summary of how this work contributes to reducing health inequalities. This may be something specific to the deliverable itself or may also be a high level description for how work in that particular priority area will be prioritising help for those who need it most and supporting those who find it hardest to access our services to do so.